SHIIAN workplan 2018-19

| Objective | Activities | Resources | Milestones |
| --- | --- | --- | --- |
| Main work projects to be delivered |
| Ensure smooth handover of an HiAP approach into Public Health Scotland | Input to HI Commission, inform focus of HI work to include HiAP Training/support for relevant staff | Time - chair | Draft Vision paper – June Commission report – December Training – tba |
| Build capacity for HiAP in wider PH system | Training and support for relevant staff in Boards Input to FPH advocacy group on HiAP Potential session on Health in EIA | Time - chair | Meet HPMs - August Circulate offer/framework for HiAP support – December? Draft position statement for AMRCs – Sep? Possible input to meeting about Welsh legislation tba tba |
| Highlight and support SHIIAN resources | Maintain website Email updates | Time – chair and ScotPHN team | Email updates - quarterly |
| Delivery depending on resources and opportunities |
| Use HIA to ensure NTS makes a positive contribution to health | Use Transport Guide to input to National Transport strategy | Time – steering group and lead author | Scoping report/HIA report |
| Establish need for resource for HiAP work on economic policies | Scope potential for HIA guide on economic development | Time – needs lead author | Scoping paper completed |
| Establish need for resource on links between HIA and community empowerment | Scope potential for HIA guide on community empowerment | Time – needs lead author | Scoping paper completed |
| Provide resource to clarify links between HIA and policy evaluation | Work to identify opportunities/ clarify different roles of HIA and policy evaluation | Time – needs lead author | Position paper |
|  | Maintenance |
| Maintain network | SHIIAN meetings | Time - members of steering group | At least three Steering Group meetings per year |